Checklist for planning a community event

To assist your planning, this is a downloadable companion to the main document of the same name. https://victas.uca.org.au/download/635/bushfires-resources-disaster-care/9878/planning-ritual-post-trauma

| EVENT MANAGEMENT FOR A COMMUNITY EVENT IN RESPONSE TO TRAUMA |  | NOTES |
| --- | --- | --- |
| PLANNING |  |  |
| Build a planning team | Planning a large community event for an unspecified number in a short time frame requires an effective team working together. - Consult Council officers, Police, VicRoads, St. John’s Ambulance etc. - Agree on areas of responsibility, risk management protocols - Engage First Nations elders through appropriate channels - Engage leaders from community groups, ecumenical and interfaith, sports and business groups. Not all need be on planning group. |  |
| Site Selection | Identify site or sites for event, suitable for anticipated crowd: - Select site with good access to toilets - Ensure access for people living with disability - Decide whether to move the crowd from one site to another - Identify site for wet weather plan. | See UCA Assembly Disability Access Guidelines https://resources.uca.org.au/images/Guidelines-For-Disability-Access_-Final.pdf |
| Risk Management and Public Liability | - Ensure risk management plan in place - Ensure Public Liability insurance is in place for event - Identify responsibility for first aid - Identify responsibility for cleaning, site restoration - If required, plan traffic management, parking - Prepare briefing notes for volunteers, ushers, traffic marshals - St. John’s Ambulance booked, or enrol current First Aiders, prepared with up to date kits. | When organising an event with any organisations other than the Uniting Church, if evidence of public liability cover is required, a ‘Certificate of Currency’ can be obtained from the Synod’s Insurance Team by emailing the Insurance Officer at: insurance@victas.uca.org.au or calling 03 9116 1995. |
| Enrol specialist personnel | In an ideal world you would draw on people with the following expertise: - Stage Manager, to conduct rehearsal and guide event - Site Manager, see logistics section - Counsellors, pastoral carers. |  |
| Shape of Gathering | Orient focus to create sense of community, assuming seating is movable: - Wide and close, rather than long and distant - Try for curved lines of seating over straight lines. Prioritise good sight lines over acoustics, and - Bring in more PA, if needed. |  |
| Ritual Action | Plan appropriate Ritual Action: - Consider several options before selecting one action - Select one element as the symbol for ritual action - Plan what people will be invited to do. Ensure people with disabilities can participate - Factor in time, between collecting element and enacting the ritual action. You may invite people to reflect with their element - Try out the ritual action in your planning group and review. If you are not happy with it, don’t be afraid to try a new idea - Decide whether there will be one focal point or several ‘stations’ in the space where the crowd can move to enact ritual action - Plan how/where the elements will be contained (baskets, bowls, tubs, etc.), and presented respectfully - Organise collection of sufficient elements well ahead of time - Plan what will happen with the elements after the event - Consider/consult on whether filming or photography will be allowed. |  |
| Spatial Coherence | To enhance focus on Ritual Action : - Identify what distractions need to be removed from the space - Select colour elements – banners, cloths, to support the ritual action. Restrict colour to one or two relevant colours - Plan and order in equipment required to rig anything at height - Design focal points where ritual action takes place. Ensure plinths or tables are accessible to all. |  |
| Speaker Preparation | Suggestions to guide speakers: - Request First Nations elder to provide the Welcome to Country, or identify person to make an Acknowledgement of Country - Reduce the number of different speakers - Give speakers time limit and/or word count guidance and encourage speakers to time themselves prior - Suggest a format for speakers to adopt, e.g. informal/formal - Keep introductions to a minimum - Prepare spoken invitation and demonstration of ritual action - Advise the time you need speakers to arrive for a sound check. |  |
| Crowd management | Prepare your ushers well with written and spoken briefing notes: - Enrol ushers with defined tasks to assist crowd management - Ensure pathways remain unimpeded throughout event - Place signage to reserve seating - Identify and communicate directions for people to move through to enact Ritual Action - Communicate location of amenities, First Aid, fire exits and extinguishers - Maintain quiet space after the event - Do not remove symbols; don’t extinguish candles, if used - Request counsellors/pastoral carers be present during and after the event. |  |
| Logistics Personnel | Ensure risk management plan is ready for action, check all required insurances are in place: - Get expert assistance and book/organise equipment to rig any elements safely at height - Consider engaging separate set up and bump out teams - Prepare a run sheet for everyone - Create a contact list with everyone’s phone details - If you do not have a dedicated stage manager, identify one person for this role. |  |
| SITE PREPARATION |  |  |
| Declutter | - Clear the space as planned see Spatial Coherence section |  |
| Visual props, banners | - Best rigged by expert in a cleared space |  |
| Seating/ standing zones | - Set up seating and/or mark-out standing zones |  |
| Access pathways | - Mark off with chalk or high-vis tape |  |
| Sight lines | - Stagger seating rows and test for sight lines |  |
| Focus lighting | - Ensure focal point/s for ritual action are well lit |  |
| Test sound/ Public Address | - Cue any recorded music or other sound files |  |
| Projection | - Cue any projected visuals |  |
| Fire and Safety protocols | - Check signage, safety plans, first aid, toilet provision, parking and traffic management are in accordance with local Council, Police etc. |  |
| REHEARSAL |  |  |
| Rehearse music | - Schedule a separate, earlier rehearsal for musicians |  |
| Rehearse ritual action | - If possible, walk through ritual action with ushers, and any speakers/ dignitaries available |  |
| Rehearse speakers | - Orient, welcome speakers, indicate where they will sit and when to move forward to speak - Adjust height of mikes, sound check each speaker. |  |
| THE EVENT BEGINS, MAY ALL YOUR PLANS GO WELL |  |  |
| AFTER THE EVENT |  |  |
| Don’t rush to clean up | - Keep the space open. People will likely return - Some ushers and counsellors remain in the space - Allow the elements of the Ritual Action to be present for some time after the event. |  |
| Photography | - If photography was disallowed during event, now may be a more appropriate time - You may want to document the event and stage a re-enactment of the Ritual Action with one or two people. |  |
| ‘Bump Out’ | - Always faster than setting up - Consider organising a fresh team of volunteers. |  |
| Memorialising | - You may have planned to retain and preserve some of the ritual elements for the future - Depending on what you decide, there may be a task to respectfully dispose of some or all of the elements. |  |
| Site Restoration | - Clean up litter - Recycle where possible. |  |
| ‘Thank you’ | - Remember to thank all your volunteers and persons/organisations involved - Acknowledge the planning team. |  |

Further contact

Nigel Hanscamp

Director – Priorities, Focus and Advocacy

Equipping Leadership for Mission eLM

29 College Cres, Parkville 3052

t (03) 9340 8816 | m 0438 732 226  nigel.hanscamp@victas.uca.org.au